## Slide 1
SmartCare-AI
Intelligent Healthcare Platform
Software Project Management – Final Year Project Presentation
University of Management and Technology, Lahore | Department of Computer Science | Fall 2022
Project Team
Zain Ul Abedeen
Asim Abdullah
Usman Suleman
Yasir Shezaad
Hamial Zaheer

## Slide 2
Agenda
SmartCare-AI | University of Management and Technology, Lahore | Fall 2022
01
Project Overview & Objectives
02
Process Model – Agile (Scrum) with Justification
03
Scope, Requirements & Deliverables
04
Risk Management (Project / Process / Resource)
05
Effort Estimation & Scheduling
06
Team Roles & Responsibilities
07
System Architecture & Key Features
08
Testing & Quality Assurance
09
Working Demo
10
Conclusion & Q&A

## Slide 3
Project Overview & Problem Statement
SmartCare-AI | University of Management and Technology, Lahore | Fall 2022
Problem
Fragmented healthcare workflow in Pakistan
No reliable first-point symptom guidance
Unverified practitioners (quackery) risk patient safety
Manual payments lack transparency & verification
No bilingual (English + Roman Urdu) system exists
Solution – SmartCare-AI
AI-powered triage assistant (English + Roman Urdu)
Admin-verified provider marketplace
End-to-end appointment lifecycle management
Manual payment proof submission + admin validation
Clinical notes, prescriptions & audit trails

## Slide 4
Process Model: Agile (Scrum) – Why?
SmartCare-AI | University of Management and Technology, Lahore | Fall 2022
Sprint
Planning
Daily
Standup
Sprint
Execution
Sprint
Review
Retrospective
(Repeat per Sprint → Release after each Sprint)
Justification: Why Agile over Waterfall?
Evolving Requirements
AI guardrails, bilingual support, payment flows were refined iteratively — not fully known upfront
Iterative Supervisor Feedback
Sprint reviews gave supervisor checkpoints after each module (auth, booking, AI, payments)
Modular Architecture
Patient, Provider, Admin portals are independent modules — ideal for parallel sprint execution
Risk Reduction
Short 2-week sprints surfaced integration issues early (Redis locking, LLM latency, RBAC gaps)
Working Demo Each Sprint
Examiner can see incremental working software — not a paper design only

## Slide 5
Project Scope & Requirements
SmartCare-AI | University of Management and Technology, Lahore | Fall 2022
In Scope
User registration, OTP verification, JWT session
Patient & Provider onboarding portals
AI triage chat (English + Roman Urdu)
Provider search, filter, geospatial ranking
Appointment lifecycle (state machine)
Manual payment proof upload + admin verify
Clinical notes, prescriptions, acknowledgment
Admin analytics & payout management
Out of Scope (Future)
Voice AI interaction (STT/TTS) – planned future
Automated online payment gateway (Stripe)
Mobile native application (iOS / Android)
Multi-language beyond English and Roman Urdu
Telemedicine / video consultation module
Key Deliverables: FYP Report | Working Web Application | API Documentation | Testing Report | Live Demo

## Slide 6
Risk Management
SmartCare-AI | University of Management and Technology, Lahore | Fall 2022
Risk
Description
Category
Likelihood
Mitigation
Scope Creep
New features (voice AI, payment gateway) added mid-development
Project-Based
High
Freeze scope after Sprint 2; log change requests separately
Schedule Delay
Unexpected LLM API latency and Redis configuration delayed milestones
Project-Based
Medium
Buffer sprints; daily standup flags blockers early
Integration Failure
React frontend and FastAPI backend integration breaks between sprints
Project-Based
Medium
Continuous integration with shared API contracts from Sprint 1
Unclear Requirements
AI guardrail rules and bilingual behavior were not fully specified initially
Process-Based
High
Use case documents (20 UCs) approved by supervisor before coding
Inadequate Testing
Manual payment flow and concurrent booking hard to test without Redis mock
Process-Based
Medium
Dedicated test sprint; BVA on OTP TTL and slot lock TTL boundaries
Documentation Lag
Report updates delayed because coding took priority in final sprints
Process-Based
Medium
Assign 1 member per sprint to sync report with latest implementation
Team Member Unavailability
Member unavailable due to exams, illness, or personal commitments
Resource-Based
Medium
Every member briefed on all modules; tasks distributed across 2 members
LLM API Cost / Limits
External LLM API rate limits exceeded during development or demo
Resource-Based
High
Cache common queries; use mocked responses in non-demo testing
Hardware / Internet
Demo environment fails due to poor internet or laptop issue on presentation day
Resource-Based
Low
Pre-load demo on 2 devices; use offline static mode as fallback

## Slide 7
Effort Estimation & Project Schedule
SmartCare-AI | University of Management and Technology, Lahore | Fall 2022
Sprint Plan (6 Sprints × 2 Weeks = 12 Weeks)
Sprint
Weeks
Key Deliverables
Lead Members
Sprint 1
Wk 1–2
Auth, OTP, JWT, RBAC setup, DB schema
All
Sprint 2
Wk 3–4
Patient & Provider onboarding, health profile
ZUA, AA
Sprint 3
Wk 5–6
AI triage (RAG, guardrails, bilingual), provider search
US, YS
Sprint 4
Wk 7–8
Appointment lifecycle, Redis slot locking, payment proof
HZ, ZUA
Sprint 5
Wk 9–10
Clinical notes, prescriptions, admin analytics, payouts
AA, US
Sprint 6
Wk 11–12
System testing, BVA, integration fixes, demo preparation
All
Effort Summary
Total Duration: 12 Weeks
Team Size: 5 Members
Est. Person-Hours: ~600 hrs (5 × 120 hrs)
Sprints: 6 Sprints × 2 Weeks

## Slide 8
Team Roles & Responsibilities
SmartCare-AI | University of Management and Technology, Lahore | Fall 2022
Every team member is fully briefed on: Project Solution, Risk Management, and Project Proposal.
1
Zain Ul Abedeen
Project Manager / Backend Lead
Sprint planning, API architecture (FastAPI), RBAC, JWT, DB schema, team coordination
2
Asim Abdullah
Frontend Lead
React + TypeScript portals (Patient, Provider, Admin), UI/UX, component design
3
Usman Suleman
AI & Integration Engineer
LLM integration, RAG pipeline, bilingual detection, pgvector search, AI guardrails
4
Yasir Shezaad
Backend Developer / QA Lead
Appointment state machine, Redis concurrency, payment workflow, test case execution
5
Hamial Zaheer
Database & Documentation Engineer
PostgreSQL schema, ORM migrations, data dictionary, report writing, deployment setup

## Slide 9
System Architecture & Key Features
SmartCare-AI | University of Management and Technology, Lahore | Fall 2022
Frontend
React + TypeScript + Vite
Patient Portal | Provider Portal | Admin Console
Backend
FastAPI (Python) + SQLAlchemy
REST API | JWT Auth | RBAC | Redis Locks | Celery
Data & AI
PostgreSQL + pgvector + LLM API
User Data | Clinical Records | AI RAG | Embeddings
AI Triage (RAG) | Verified Provider Search | Appointment State Machine | Manual Payment Proof | Clinical Notes & Rx | RBAC Security

## Slide 10
Testing & Quality Assurance
SmartCare-AI | University of Management and Technology, Lahore | Fall 2022
Unit
Testing
Integration
Testing
BVA
(Boundary)
Decision
Tables
Traceability
Matrix
Test Coverage Summary
Test Suite
Cases
TIDs
Scenarios Covered
Status
Authentication & RBAC
6 cases
TC-001–006
Registration, OTP TTL, session revocation, role enforcement
PASS
AI Triage & RAG Guardrails
4 cases
TC-007–010
Emergency override, self-harm block, context isolation, Roman Urdu
PASS
Appointment & Concurrency
4 cases
TC-011–014
Redis SETNX locking, race condition, TTL sweep, file validation
PASS
Provider & Clinical Workflow
4 cases
TC-015–018
Visibility gate, search radius, prescription timing, Rx ack
PASS
Payment & Settlement
4 cases
TC-019–022
Proof approval/rejection, overdraft block, ledger immutability
PASS
Requirements Traceability Matrix: 100% of 19 functional requirements traced to use cases and test cases.

## Slide 11
Working Demo – Solution Summary
SmartCare-AI | University of Management and Technology, Lahore | Fall 2022
Demo Flow (Live walkthrough after presentation):
1
Register as Patient
OTP verification, health profile onboarding
2
AI Triage Chat
Type symptom in English or Roman Urdu — safe guidance returned
3
Search Provider
Filter by specialty, see distance-based ranking
4
Book Appointment
Select slot — Redis lock fires, payment instructions shown
5
Upload Payment Proof
Screenshot of EasyPaisa/bank transfer uploaded
6
Admin Verifies
Admin confirms proof — appointment status → CONFIRMED
7
Provider Consultation
Provider writes notes & issues digital prescription
8
Patient Acknowledges Rx
Prescription marked ACKNOWLEDGED — audit trail complete

## Slide 12
Our Team & Conclusion
SmartCare-AI | University of Management and Technology, Lahore | Fall 2022
ZUA
Zain Ul Abedeen
AA
Asim Abdullah
US
Usman Suleman
YS
Yasir Shezaad
HZ
Hamial Zaheer
Conclusion
SmartCare-AI addresses real healthcare gaps in Pakistan through a unified, AI-assisted platform
Agile (Scrum) process model enabled iterative delivery of 6 independent modules over 12 weeks
All 9 identified risks (project, process, resource) have defined mitigation strategies
22 test cases cover 100% of in-scope requirements with full traceability matrix
Every team member is fully briefed on the solution, risks, and project proposal
Working demo follows this presentation — live end-to-end walkthrough of all 8 steps